## Deliverables
Deliverable Item | Task | % of Task Effort | Effort Estimate (Hours)
Detailed Design Documentation | Design | 70% | 31.262
Website that meets the Functional Requirements | Build | 94% | 223.799
Website that meets the Non-Functional Requirements | Design | 30% | 13.398
Unit and Integration Test Plan Document | Test | 15% | 9.408
Unit and Integration Test Results Document | Build | 4% | 9.5234
System Test Results Document | Test | 1% | 0.6272
Developer Test Certificate Document | Build | 1% | 2.3808
System Installation Manual | Documentation | 60% | 9.4416
System Administration Manual | Documentation | 40% | 6.2944
RTM Build Documentation (defects, issues etc) | Build | 1% | 2.3808
User Acceptance Signoff | Test | 4% | 2.5088
UAT/UAT support | Test | 10% | 6.272
System Testing (Automated/Manual) | Test | 70% | 43.904
|  | Total Hours: | 361.2
| Design: | 100%
| Build: | 100%
| Test: | 100%
| Documentation: | 100%

## Effort Calculations
Units of Work By Estimated Complexity | UI | Interface | Data Model | Total | Hours Modifier | Total Effort
Easy | 11 | 5 | 5 | 21 | 2 | 42
Medium | 11 | 9 | 6 | 26 | 7.6 | 197.6
Hard | 1 | 0 | 1 | 2 | 15.2 | 30.4
Complex | 2 | 2 | 0 | 4 | 22.8 | 91.2
Special Case
[6 empty] | 361.2 | Hours
Breakdown by Task | Easy | Medium | Hard | Complex | Totals |  |  | Note: Values in H8, G16 and G24 should match!
Design | 2.1 | 19.76 | 4.56 | 18.24 | 44.66
Build | 34.86 | 144.248 | 17.936 | 41.04 | 238.084
Test | 4.2 | 29.64 | 6.08 | 22.8 | 62.72
Document | 0.84 | 3.952 | 1.824 | 9.12 | 15.736
Totals | 42 | 197.6 | 30.4 | 91.2
[5 empty] | 361.2 | Hours
|  |  | Based on… |  | 38 | Hours per week
|  |  |  | Design | 1.1753 | Weeks
|  |  |  | Build | 6.2654 | Weeks
|  |  |  | Test | 1.6505 | Weeks
|  |  |  | Document | 0.41411 | Weeks
|  |  | Total |  | 361.2 | Hours
|  |  | Total |  | 9.5053 | Weeks
|  |  | Based on.. |  | 7.6 | Hours per day
|  |  |  | Design | 5.8763 | Days
|  |  |  | Build | 31.3268 | Days
|  |  |  | Test | 8.2526 | Days
|  |  |  | Document | 2.0705 | Days
|  |  | Total |  | 361.2 | Hours
|  |  | Total |  | 47.5263 | Days

## Complexity
Complexity | Design (%) | Build (%) | Test (%) | Document (%) | Total Effort (%) | Total (Hours) | Design (Hours) | Build (Hours) | Test (Hours) | Document (Hours) | Total (Hours)
Easy | 5% | 83% | 10% | 2% | 100% | 2 | 0.1 | 1.66 | 0.2 | 0.04 | 2
Medium | 10% | 73% | 15% | 2% | 100% | 7.6 | 0.76 | 5.548 | 1.14 | 0.152 | 7.6
Hard | 15% | 59% | 20% | 6% | 100% | 15.2 | 2.28 | 8.968 | 3.04 | 0.912 | 15.2
Complex | 20% | 45% | 25% | 10% | 100% | 22.8 | 4.56 | 10.26 | 5.7 | 2.28 | 22.8
Special Case
Note: The values in Column H and Column M should match!
To adjust the relative weight (hours/effort) for effort complexity, modify the hours in Column H

## Requirement Mapping
Feature Description | REQ# | UI | Interface/Integration | Schema/DB | Total Hours
Administration Utility
User Management | 1-20 | Easy | Easy | Easy | 6
Create New User | 1-3
Search for Users | 3-10
Modify/Disable Users | 10-20
Group Management | 20 - 18 | Medium | Easy | Easy | 11.6
Create New Group | 11
Search Groups | 12-15 | Easy |  |  | 2
Modify/Disable Groups
Validation | 16, 17 | Easy |  |  | 2
Group Management Workflow | 18
End-User Application | 19-29 | Medium | Easy | Easy | 11.6
Baseline Functionality
Security Rules | 19, 21
Validation | 25, 26, 29 | Easy |  |  | 2
Notification | 28 |  | Medium |  | 7.6
Manage Data | 30 - 39 | Complex | Medium | Medium | 38
Create New Data | 30, 31
Notification | 34
Search Data (non-reporting) | ?? | Complex | Complex | Hard | 60.8
View/Edit Data | 32 | Medium | Medium | Easy | 17.2
Validation | 35
Disable Data | 33 | Easy |  |  | 2
List Roles | 33
Apply Business Rules |  | Medium | Medium |  | 15.2
Data Management Workflow | ??
Create/View/Edit Project Rules | ??
Auditing
Create audit record for each DB create/update action | 275 |  |  | Medium | 7.6
Manage Audit Data |  | Easy |  |  | 2
View Items | 276
User Authentication | 40-44
Login Page | 40 | Medium | Easy | Easy | 11.6
Authentication Rules | 41,42,43,44,46
Change Password | 42 | Medium |  |  | 7.6
Authorised Data Access | 47 | Medium | Medium | Medium | 22.8
Role Membership | 45 | Medium | Medium | Medium | 22.8
Presentation Layer
Branding | 48 | Hard | Medium | Medium | 30.4
Input Validation - Date | 49, 50 | Easy |  |  | 2
Document Attachment | 51, 52, 88 | Medium | Medium | Medium | 22.8
Warning Leaving Page | 53, 54 | Easy | Easy |  | 4
Validate Pages | 55 - 59 | Medium |  |  | 7.6
Display/Update Change Audit | 60 | Easy |  |  | 2
Reporting
General Reporting
View/Print/Export/Save | 247, 250, 253 - 258 | Easy |  |  | 2
Rules | 181
Authentication Check | 148, 149 | Medium | Medium |  | 15.2
Report Data Binding | 151, 152
Individual Reports | 61-80
Data Report A | 61-68 |  | Complex |  | 22.8
Data Report B | 69-75
Data Report C | 76-80
Criteria Based Reporting
Allow creation of adhoc reports | 171-174 | Easy |  |  | 2
|  |  |  | Total Hours: | 361.2